## WBS Project CNP
Features | Days | User Stories | US Description | US Acceptance Criterias | Relative Tasks | Notes
Project management setup (Agile process) | 1.5 | Prepare AzDO organization. Boostap and configure CNP projects | . Ensure that you have Visual Studio Professional subscription. . Create Azure DevOps organization. . Using Bootstrap provision CNP projects into your Organization. | . Azure DevOps organization is created and configured. . CNP projects are bootstrapped into Organization. | Ensure that Azure DevOps organization is created
Review Bootstrap readme
Provision CNP projects in your Azure DevOps organization
|  | Project Configuration: Configure Boards. | . Review Azure DevOps Services Project settings . Review Boards configuration. . Ensure that Epics, Features and Stories navigation levels are enabled. . Review Iterations and link Default and Backlog iteration to backlog items. | . ADO project Boards are configured . Backlogs and Iterations configured as per best practices | Perform Boards/Team Configuration. Enable Epics
Perform Boards/Team Configuration. Configure Default and Backlog iteration to link to a backlog items
Configure Boards/Backlog service tab to display backlog with view (PBI type, PBI Name, assignee, Iteration Path, Story Points, Priority)
|  | Transform project WBS (excel file content) to project agile process | . Review WBS structure and elements. . Ensure all customer's requirements are covered with appropriate Product Backlog Items (PBIs) created on project's board. | . Features and User stories arecCreated in accordance with WBS structure. . Tasks for apropriate Stories are created if necessary. | Migrate excel structure to a project related product backlog items (PBIs)
Review all PBI list on the Boards/Backlog service tab
|  | Boards Configuration: Configure Sprints | . Review CSS project timeline and define number of Sprints. . On ALZ project configuration create Sprint and set dates. | . Sprints are created. . Iteration dates are defined in according to delivery timelines. | Perform Boards/Project Configuration. Create Sprints
Setup Sprints dates
Perform Boards/Team Configuration. Configure Sprints iterations
|  | Perform Sprint Planning | Ensure proper project planning and reflect this on Azure Boards continuosly by: . Reviewing obtained Features and User stories. . Prioritising items. . Estimating stories with story points. . Assigning stories to sprints in accordance with the priorities. (start 1st sprint at least) | . Features and User stories are created and prioritized. . User Stories are estimated applying required estimation strategy. . 1st sprint is planned, contains required US list | Make business priorities
Estimate user stories (put relevant story points)
Put appropriate User stories to first sprint in equilibrium of priorities and your capacity
Verify/Review all sprint's PBI on the Boards/Sprints service tab
|  | Reporting: Create and Configure Dashboards | . Review CSS PM reporting materials and configure required Project Dashboards | . Project Dashboards are configured and visible on ADO Dashboards panel. . Sprint burndown and velocity charts are added to the project dashboard. . Report of deliverables (amount of features per state) is created. | Configure Project Dashboards.
Add report of Sprint burndown chart on the project dashboard
Add report of Sprint velocity chart on the project dashboard
Add report of deliverables (amount of features per state) chart on the project dashboard
Environment preparation (Deploy accelerator) | 1.5 | Review projects. Read through projects documentation | . Observe projects. . Read projects documentation Wiki. . Review definition of goals and objectives. . Review Infra and CI/CD designs and documentation. . Dive dipper into CNP documentation. | . Project documentation is reviewed. . Goals and objectives are clear. . Infra and CI/CD designs and documentation are clear. | Review CNP Projects
Read through Projects documentation
Review infrastructure design
Review CI/CD design
|  | Configure CNP projects | . Setup Azure DevOps organization and CNP projects. | . Service connection and Variable groups are configured. . Setup of Terraform config and mudules are done. . Required Azure DevOps extentions are installed. . Setup of Pipelines and Approvals is done. | Create Service connections
Setup Variables and Variable groups
Update Pipelines configuration
Setup Terraform config and modules
Install required AzDO extentions
Configure approvals
|  | Deploy infrastructure | . Get details about Infra management tools. . Deploy CNP infrastructure. | . Infra management tools are reviewed. . Step to deploy and destroy infrastructure are clear. . Pipelines are prepared to deploy required infra and components. . CNP infrastructure is up and running. | Review Terraform configuration and Pipelines
Get the details about deploying and destroying of infrastructure.
Spin up infrastructure using Infra pipelines
Review infrastructure resources and configuration
Delivery velocity improvement (Trunk-based) | 4 | Re-work CI/CD design to meet Trunk-based strategy | Prepare new version of CI/CD design to meet Trunk-Based development strategy. It should be done according to the Project requirement and expectations described in a wiki - 02_Software_Delivery_Velocity | . Software delivery velocity, delivery schemas and other documentation are reviwed and analyzed. . CICD design is prepared. It includes necessary diagram, drawings (draw.io, visio) which show desired improvements . Enhancement implementation plan is prepared and contains detailed to-do instructions . The implementation plan and design match the expected requirements and best practises. | Review CI/CD design and trunk-based documentation
Prepare new CI/CD design based on trunk-based strategy
Plan migration activities
|  | Setup pipelines and policies | Enroll necessary CICD pipelines modification to update company's delivery leverage to improve its velocity. The policies should be also updated according to the Trunk-Based strategy | . CI\CD pipelines are updated according to the trunk-based migration plan. . The modified CICD pipelines are functional. It should match delivery improvement requirements and expectation. . The solution follows DevOps best practises. | Update pipelines branch and trigger configuration
Test Trunk-based CI\CD pipelines
|  | Update branches configuration in accordance with the new strategy | Branch and repo policies should be fully reconfigured to accomplish migration process to Trunk-based strategy | . Branches and repos policies are reconfigured according to the Trunk-Based strategy. . The full TBD based CI\CD strategy is tested. It should match delivery improvement requirements and expectation. . The solution follows DevOps best practises. | Setup policies for trunk, release and feature branches
Update branching schema according to the trunk-based model
Conduct TBD based strategy CI¦CD schema testing for all possible flows (feature, main, release)
Code quality/stability improvement (Shift left testing) | 7 | Discover dynamic feature environment (DFE) and plan future steps | . Get familiar with Shift-left testing concepts. . Review and understand goals and problem what you are going to solve. . Deep dive into Dynamic feature environment. . Plan further activities. It should be done according to the Project requirement and expectations described in a wiki - 03_Software_Quality_And_Stability | . Documentation is reviewed. . Problem statement and goals are clear. . Further activities are defined and planed according to DFE requirements. | Deep dive into Shift-left testing documentation.
Review problem statement, requirements, and goals.
Plan Dynamic feature environment (DFE) implementation steps.
|  | Implement Dynamic feature environment | . Adopt pipelines to support DFE deployment. . Setup pipelines definition, variables groups, etc. . Improve pipelines approval process. | . You have a pipelines which support DFE deployment. . Approval process in configured in accordance with requirements. | Update pipelines to support DFE deployment
Setup DFE related variable groups
Modify deployment approval process
|  | Setup automated tests | . To implement Deployment verification tests to detect that application is correctly deployed. . Implement Helm tests | . Deployment verification tests are implemented in accordance with requirements. . CI/CD supports Helm charts testing. | Implement Deployment verification tests
Implement Helm tests
Zero-downtime deployment | 6 | Review Zero-Downtime deployment strategy and Canary deployment approach. Create Canary implementation plan | . Get familiar with Zero-Downtime deployment strategy concept. . Investigate Canary deployment implemenation in Kubernetes as one of the possible option for Zero-Downtime. . Prepare detailed Canary implementation plan according to suggested approach. It should be done according to the Project requirement and expectations described in a wiki - 04_Zero_Downtime | . Documentation is reviewed. . Problem statement and goals are clear. . You are ready to describe how Canary and Zero-Downtime deployment correspond to each other. . Canary implemenattion plan created and represents all necessary steps. | Review Zero-Downtime and Canary deployemnt consept
Investigate Canary deployment implemenation in Kubernetes
Define detailed Canary inmplementation plan
|  | Implement Canary deployment | . Supplement application deployment pipeline with Canary deployment option for Production environment. . Update pipeline templates and helm charts libraries to support Canary approach. | . Application deployment pipeline supplemented with Canary deployment. . Pipeline templates and Helm charts libraries updated accordingly. . The pipeline supports manipulation of traffic percentage that should go to Canary instances versus Stable one. . The number of Stable and Canary instances is changing depending on the traffic that should be covered by them. . Canary deployment approach meets all aspects that represented in appropriate guide within documenattion. | Supplement application pipelines with Canary deployment steps, update pipeline templates.
Adjust Helm charts to support Canary deployment
Test Canary deployment flow
|  | Update Canary deployment solution with zero-dowtime option | . Adjust Kubernetes deployment configuration to ensure that Production deployment happens with zero-downtime. | . Production release is happening without service interuption or quality downgrade. . Zero-Downtime implementation approach meets the guide within documenattion or alternative solution that garanties service zero-downtime. | Implement Zero-Downtime logic for Canary deployment
Test Canary deployment flow with Zero-Downtime
Total Effort for the Scope, Days | 20